## Prelims - 20 Wks
Staff | [6 empty] | COST
Role | Nr of days a week | % | From Wk | To Wk | Nr Weeks | Rate | TOTAL
OPERATIONAL
Project Manager | 5 |  |  |  | 0 | 2000 | 0
Site Manager | 5 |  |  |  | 0 | 1500 | 0
Section Manager | 5 |  |  |  | 0 | 1000 | 0
Production Trainee | 5 |  |  |  | 0 | 0 | 0
ENGINEERING
Project Engineer | 2 |  |  |  | 0 | 2000 | 0
PLANNING
Planner | 1 |  |  |  | 0 | 2000 | 0
DESIGN
Design Manager | 3 |  |  |  | 0 | 2000 | 0
Sustainability Manager | 1 |  |  |  | 0 | 2000 | 0
BIM Manager | 1 |  |  |  | 0 | 2000 | 0
BUILDING SERVICES
Senior Building Services Manager | 3 |  |  |  | 0 | 2000 | 0
COMMERCIAL
Project Surveyor | 5 |  |  |  | 0 | 2000 | 0
Site Surveyor | 3 |  |  |  | 0 | 1500 | 0
Assistant Surveyor | 5 |  |  |  | 0 | 1000 | 0
ADMIN
Site Secretary | 2 |  |  |  | 0 | 1000 | 0
Total to summary | [6 empty] | 0
% of Project Value
Number of Staff
Weekly run rate
Please Note: The costs being using are not reflective of pay and just for illustative purposes in this example

## Programme
Programme - Resource Chart
| Week Nr | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
OPERATIONAL
Project Manager
Site Manager
Section Manager
Production Trainee
ENGINEERING
Project Engineer
PLANNING
Planner
DESIGN
Design Manager
Sustainability Manager
BIM Manager
BUILDING SERVICES
Senior Building Services Manager
COMMERCIAL
Project Surveyor
Site Surveyor
Assistant Surveyor
ADMIN
Site Secretary